## People View
Week | Week Starting | PH | DM | BP | Milestone | Notes
14 | 2017-04-03 | Data loader testing | SQL Server middleware | SQL Server middleware | CDC sandbox ready
15 | 2017-04-10 |  |  |  | Study submission running on SQL server
16 | 2017-04-17 | Assist with middleware (database fixes); SQL Server full install testing
17 | 2017-04-24 |  |  |  | SQL Server RIF complete
18 | 2017-05-01 | CDC Install | CDC Install |  | CDC Install
19 | 2017-05-08 | Assist with middleware (database fixes); SQL Server full install testing | Risk analysis statistical requirements
20 | 2017-05-15
21 | 2017-05-22 |  | Assist with middleware (database fixes); SQL Server full install testing | SQL Server Data Loader
22 | 2017-05-29 |  |  | Holiday
23 | 2017-06-05 |  | JRI | SQL Server Data Loader
24 | 2017-06-12 |  |  | Risk analysis R scripts
25 | 2017-06-19 | JRI Integration |  | SQL Server Data Loader
26 | 2017-06-26 | Penetration testing | Risk analysis middleware |  | CDC penetration test passed | WILL SLIP
27 | 2017-07-03 | Holiday |  | SAHSU RIF data statistical testing | PHR Demo 3rd July
28 | 2017-07-10 | http://www.geopedia.si/lite.jsp?params=T118_x408210_y126301_s14#T118_F11063:8283_x405158_y123863_s15_b4 | GIS Course
29 | 2017-07-17 | More holiday | Holiday | Non RIF project work
30 | 2017-07-24
31 | 2017-07-31 | Cloud service, SEER data | Risk analysis middleware
32 | 2017-08-07 | Data Loader testing and manual |  | Holiday
33 | 2017-08-14 |  |  | Non RIF project work
34 | 2017-08-21
35 | 2017-08-28 | SEER, Halland Test Data load
36 | 2017-09-04 | Risk analysis integration
37 | 2017-09-11 |  |  |  | Risk analysis
38 | 2017-09-18 | Data Loader testing and manual | RIF middieware logging | Non RIF project work, assist PH with Data loader
39 | 2017-09-25
40 | 2017-10-02 |  | IRF middleware code tidy
41 | 2017-10-09 | Background tile download (cache support)
42 | 2017-10-16
43 | 2017-10-23 | UK COA 2011 tiles
44 | 2017-10-30
45 | 2017-11-06
46 | 2017-11-13 | Big Data, Small Area |  |  | SAHSU 30th
47 | 2017-11-20 | SAHSU RIF install | SAHSU RIF install | SAHSU RIF install
48 | 2017-11-27 | SAHSU RIF initial data load |  | SAHSU RIF data load
49 | 2017-12-04 |  |  |  | SAHSU RIF operational
50 | 2017-12-11
51 | 2017-12-18
52 | 2017-12-25
|  |  |  | Issses: | No SAHSU RIF operational for 30th. It can be made operational if we shift focus from the data loader
No Statistical testing has been programmed in
No public network demonstrator system
|  | 2 days/month minimum management |  |  | No allowance for CDC install support
Formulas:
Week Starting = DATE(2017,1,-2)-WEEKDAY(DATE(2017,1,3))+[Week]*7

## 2018 Tasks
Add support for missing features: | Who | Kev 2.0 time | DM | PH | BP | Estimate (weeks) | Likely to be lost if no Kev 2.0
Multiple investigations | DM with PH for DB |  | 2 | 1 |  | 3
Multiple covariates per investigation | DM with PH for DB |  | 4 | 1 |  | 5
ICD 9, ICD oncology, HES OPCS and A+E codes | Kev 2.0 | 4 | 1 |  |  | 5 | YES, possibly ICD 9 only
Use of pre-defined code lists | DM |  | 3 |  |  | 3
Low birth weight analysis support | DM |  | 3 |  |  | 3
Risk analysis related functionality (e.g. Mantel–Haenszel test) | DM and BP |  | 3 |  | 1 | 4
SATSCAN integration | DM |  | 4 |  |  | 4 | Support only (i.e. run externally) also possible
BayeSTDetect | DM and BP |  | 8 |  | 4 | 12
RIF user manual | DM and BP |  | 2 |  | 2 | 4
IG Tool (includes documentation) | Kev 2.0 | 16 |  |  |  | 16 | YES. Will be done using SQL; time needed to document
Web based/more functional data loader (includes documentation) | Kev 2.0 | 24 |  |  |  | 24 | YES. Will have current limited functionality
Complete tilemaker (includes documentation) | PH |  |  | 16 |  | 16 | Will be under pressure compensating for lack of Kev 2.0
RIF batch (includes documentation) | DM/PH |  | 6 | 2 |  | 8
Comprehensive statistical test suite (includes documentation) | BP |  |  |  | 8 | 8
Papers!!!! | All | 2 | 2 | 2 | 2 | 8
Use on real study | Becky 2.0 |  |  | 2 | 2 | 4
SAHSU data load and setup (includes documentation) | PH |  |  | 4 |  | 4
| Totals |  |  |  |  | 131
| Kev 2.0 total time | 46
| DM total time |  | 38
[Note that 28 weeks at 14 days/month = 40 weeks] | PH total time |  |  | 28
| BP total time |  |  |  | 19