## Task View
Month | Milestone | Task | Sub task | Who | Period start | Period end | Planned days | Actual Start | Actual end | Sub Task dependent on | Details
July |  | 1: R |  | KG/BP | 2016-07-11 | 2016-08-12 | 15+10 | 2016-07-01 |  |  | Integrating R into Java middleware. The use of ODBC limits the RIF backend to Windows only is acceptable; rework to support Postgres/Linux (i.e. the Private Network) is deferred to next year. R dependencies (e.g. R_HOME), location of R scripts will need to be handled; the ODBC connection must be the system type with no hard coded username and password; this will be provided by the Java interface. From the database viewpoint it must be a single transaction; i.e. it all works or leaves no trace. Records being updated (e.g. rif40_studies) must be locked (i.e. SELECT … FOR UPDATE …) at transaction start. A realtime status update using a second transaction is NOT required, this is part of performance tuning next year.
|  | 2: Web services | [8 empty] | Complete middleware web services; port Postgres web service support functions to Java middleware to make portable to SQL Server
July |  |  | 2.1 Middleware services planning | KG | 2016-07-25 | 2016-07-28 | 1 |  |  |  | A complete list of web services provided by the middleware to be provided by Kev by 12/7/2016. This should detail is the services are a) not yet coded, b) coded portably or use c) RIF database or d) Postgres specific function(s). DM to check that this provides all the services he requires.
|  |  | 2.2 Database services port list | PH | 2016-07-28 | 2016-07-19 | 1 |  |  | 2.1 Middleware services planning | PH will then check this list against the database, and any example SQL supplied for portability. He will then assess the porting work required and produce a priority work order list for David and Kev. When this list completes (target to be set: hopefully mid-September) there will be no Postgres dependencies in the front end or the back end – this largely determines whether the December deadline will work.
|  |  | 2.3 Taxonomy services | KG | 2016-07-01 | 2016-07-19 | 3 | 2016-07-01 | 2016-07-18 |  | ICD 10 support only at this point
July, August |  |  | <ADD list of middleware services to be ported> | KG/DM | 2016-08-01 | 2016-09-03 | 14 each |  | # |  | Estimate is probably too low
|  | 3. Shapefile services |  | PH | [6 empty] | PH will work on the shapefile services; with a target of end September to be ready for dataloader integration. This date should be regarded as at risk now that I am managing the team; I will request an additional 4-6 days consultancy per month of effort from September onwards.
July |  |  | 3.1 Meta data | PH | 2016-07-01 | 2016-07-29 | 6 | 2016-07-01 |  |  | Complete meta data entry; ready spatial data: create multi polygons, spatial primary key (Gid); WKT support; batch mode and status update;
August |  |  | 3.2 Geospatial outputs | PH | 2016-07-29 | 2016-08-31 | 12 |  |  | 3.1 Meta data | Map tile generator, Geolevel intersction generator
September |  |  | 3.3 Get Methods | PH | 2016-08-31 | 2016-10-07 | 12 |  |  | 3.2 Geospatial outputs | Methods to return data fromn web service to web front end/Java middleware
TBD |  |  | 3.4 Performance scaleability | PH |  |  | 8 |  |  |  | Performance scaleability (e.g. US census tract, UK cesnsus output area support)
July |  | 4. Study submission |  | DM
|  |  | 6.1 Taxonomy services | DM | 2015-07-25 | 2016-07-29 | 1 |  |  | 2.3 Taxonomy services | Integate middleware Taxonomy services
|  |  | 6.2 Database logon | DM | 2015-07-25 | 2016-07-29 | 2 |  |  |  | Database logon needs to be modified to prevent session hijacking
<ADD any middleware services required>
|  |  | <ADD more tasks> | DM
July, August |  | 5. Results viewer | <ADD list of middleware services required> | DM | [5 empty] | 4. Study submission
|  |  | <ADD more tasks> | DM
|  | 6. Database port consistency |  | KG/PH/MD | [6 empty] | From early September Kev will move to working on the dataloader; using only SQL server. This requires that the SQL server database schema is ready and is the same as Postgres. Small changes are required to support Postgres datbase patches
July |  |  | 6.1 Schema comparison | KG/MD | 2016-07-01 | 2016-07-29 | 3 |  |  |  | The two databases must have: o The same tables and columns (the table rif40_tables_and_columns); o The same primary and foreign keys – i.e. the same relational integrity checks; o The same indexes; o Partitioning is NOT required – this is a performance tuning feature deferred to next year
August |  |  | 6.2 SQL server schema completion | PH/MD | 2016-09-12 | 2016-09-23 | 5 |  |  |  | Make database ports the same. Missing INSERT/UPDATE/DELETE triggers will probably be deferred to next year.
October to December |  | 7. Data Loader |  | KG |  |  | 25 |  |  |  | All work until December to be done on SQL server only; ideally should be tested using the same test dataset as the statistical package. Better estimates needed
|  |  | 7.0 SQL server porting |  |  |  | 5 |  |  | 6.2 SQL server schema completion
|  |  | 7.1 Numerator |  |  |  | 5 |  |  | 8.1 US Test dataset
|  |  | 7.2 Denominator |  |  |  | 5 |  |  | 8.1 US Test dataset
|  |  | 7.3 Covariates |  |  |  | 5 |  |  | 8.1 US Test dataset
|  |  | 7.4 Geospatial data |  |  |  | 20 |  |  | 3. Shapefile services
September to December |  | 8. Statistical testing |  | BP
|  |  | 8.1 US Test dataset | [7 empty] | Required to county level; synthetic datasets are also a possibility. Might consider using SEER data.
8.2 Test Plan
|  |  | 8.3 Manual calculation of tests | [7 empty] | For verification
Milestone Summary
September | Study Submission | [8 empty] | 4. Study submission
September | Results Viewer | [8 empty] | 5. Results viewer
December | Data Loader | [8 empty] | 7. Data Loader
December | Study submission and Results viewer running on SQL server | [8 empty] | 7. Data Loader
Formulas:
Period start = [Period end, row above]

## People View
Week | Week Starting | PH | KG | DM | BP | MD | Milestone | Notes
27 | 2016-07-04 | Shapefile services: 3.1 meta data (6 days) | 2.3 Taxonomy services (4 days) | Data Viewer | Integrate R into Java middleware (10 days)
28 | 2016-07-11 |  |  | Exposomics
29 | 2016-07-18 |  | Integrate R into Java middleware (5 days) | GIS short course | Holiday
30 | 2016-07-25 |  | 2.1 Middleware services planning | Disease Mapping - m/w services (5 days) |  |  | Study Submission
31 | 2016-08-01 | Shapefile services: 3.2 Geospatial outputs (8 days) | Integrate R into Java middleware (10 days) | Handover to new GIS person | Integrate R into Java middleware (10 days)
32 | 2016-08-08 |  |  | Data Viewer - middleware services (5 days)
33 | 2016-08-15 | Holiday | 6.3 Middleware services - create study (14 days) | Holiday | Holiday
34 | 2016-08-22 | Shapefile services: 3.2 Geospatial outputs II (4 days) |  | 6.1 Taxonomy services, 6.2 Database logon
35 | 2016-08-29 | Shapefile services: 3.3 Get Methods I (6 Days) |  | 6.3 Middleware services - other (4 days) [Potentially Kevin as well] | Not allocated | Holiday to 5th September | Results Viewer
36 | 2016-09-05 |  | Not allocated (for overrun - 10 days) | Allocated to JG | 8.1 US Test dataset, 8.2 Test Plan, 8.3 Manual calculation of tests | 6.1 Schema comparison (3 days)
37 | 2016-09-12 | 6.2 SQL server schema completion (5 days) |  | 6.3 Middleware services - other (10 days) [Potentially Kevin as well] |  | 6.2 SQL server schema completion (5 days)
38 | 2016-09-19 |  | ALSPAC
39 | 2016-09-26 | Shapefile services: 3.3 Get Methods II (6 Days)
40 | 2016-10-03 |  |  | Allocated to JG
41 | 2016-10-10 | Not allocated (for overrun - 9 days) | 7. Data Loader (35 days) | Not allocated (for overrun - 15 days)
42 | 2016-10-17
43 | 2016-10-24
44 | 2016-10-31 | 3.4 Performance scaleability (8 days) |  | Allocated to JG | Documentation
45 | 2016-11-07 |  |  | Not allocated (for overrun - 15 days)
46 | 2016-11-14
47 | 2016-11-21
48 | 2016-11-28 | Not allocated (for overrun - 4 days) |  | Allocated to JG
49 | 2016-12-05 | FINAL INTEGRATION |  |  |  |  | Data Loader
50 | 2016-12-12 | Not allocated (for overrun) | Not allocated (for overrun) | Not allocated (for overrun) |  |  | Study submission and Results viewer running on SQL server
51 | 2016-12-19
52 | 2016-12-26
1 | 2017-01-02
2 days/month minimum management
Formulas:
Week Starting = DATE(2016,1,-2)-WEEKDAY(DATE(2016,1,3))+[Week]*7

## Postgres functions summary
Postgres schema | Function | Description | Middleware port | SQL Server Port work | Cursors | Time Estimate (Days)
<user> | rif40_run_study() | Allows batch to run study as user; not required | NO | NO
rif40_dmp_pkg | 1 function | CSV creator, not required | NO | NO
rif40_geo_pkg | 35 functions | Prcoess geospatial load data into RIF tables and creates map tiles. Replaced by shapefile web services and data loader | NO | NO
rif40_log_pkg | 9 functions | Logging support; not required | NO | NO
rif40_sm_pkg | _rif40_create_disease_mapping_example(character varying, character varying, integer, character varying, text[]) | Execute disease mapping exmaple SQL statement, register with test harnes | NO | NO
| cleanup_orphaned_extract_and_map_tables(boolean) | Cleanup and map and extract tables not referenced by a study (runs as rif40; testing purposes only) | NO | NO
| rif40_clone_study(integer) | Clone study [testing purposes only] | NO | NO
| rif40_compute_results(integer) | Compute dummy results (observed only) from extract table. Create map table. Populates tables for R. Runs as RIF40, grants to user, must be a database procedure | YES | YES | 6 | 2
| rif40_create_disease_mapping_example(character varying, character varying, character varying, character varying, character varying, character varying[], character varying, character varying, character varying, character varying, integer, integer, character varying[], character varying[], character varying[], character varying, character varying) | Create disease mapping example; testing purposes only | NO | NO
| rif40_create_extract(integer) | Create extract table. Calls rif40_study_ddl_definer() to create table rif40_insert_extract() to populate extract table. | YES | YES | 5 | 2
| rif40_create_insert_statement(integer, character varying, integer, integer) | Create INSERT SQL statement. SQL will need tuning for SQL server | YES | YES | 8 | 3
| rif40_delete_study(integer) | Delete study from tables | YES | NO | 1 | 0.3
| rif40_execute_insert_statement(integer, character varying, character varying, integer, integer) | Execute INSERT SQL statement | YES | NO | 3 | 0.7
| rif40_insert_extract(integer) | Insert data into extract table. Calls: rif40_create_insert_statement(), rif40_execute_insert_statement() | NO | NO | 2 | 1
| rif40_rename_map_and_extract_tables(integer, integer) | rename <old study id> extract and map tables to <new study id> extract and map tables; used for testing; now obsoleted by partitioning because partition movement is not supported. | NO | NO
| rif40_reset_study(integer) | Reset study to the 'C' (created state) so it can be re-run; testing purposes only | NO | NO
| rif40_run_study(integer, integer) | Run study. Calls: rif40_create_extract(), rif40_compute_results(). Verification to be removed. And rif40_verify_state_change() functionality merged. | YES | NO | 1 | 0.3
| rif40_study_ddl_definer(integer, character varying, character varying, character varying[]) | Execute DDL statements as RIF40 (so the user cannot control access to extracted data), must be a database procedure | YES | YES | 5 | 1.5
| rif40_verify_state_change(integer, character varying, character varying) | State change function/checking functions | YES | NO | 5 | 3
Total |  |  | 9 |  | 36 | 13.8
rif40_sql_pkg | 57 functions | Used by other function; DB test harness, DB build; partitioning; not required | NO | NO
rif40_trg_pkg | 6 functions | Trigger support; already implemented in SQL server | NO | NO
rif40_xml_pkg | _populate_rif40_tiles_explain_ddl(character varying, integer, character varying) | Postgres specific performance tuning function. Coerce EXPLAIN output into a table with a known column | NO | NO
| _rif40_createmapareaattributesource_explain_ddl(character varying, character varying, character varying) | Postgres specific performance tuning function. Coerce EXPLAIN output into a table with a known column | NO | NO
| _rif40_geojson_explain_ddl(character varying, character varying, character varying[]) | Postgres specific performance tuning function. Coerce EXPLAIN output into a table with a known column | NO | NO
| _rif40_geojson_explain_ddl2(character varying, real, real, real, real, character varying) | Postgres specific performance tuning function. Coerce EXPLAIN output into a table with a known column | NO | NO
| _rif40_get_geojson_as_js(character varying, character varying, character varying[], integer, boolean, integer, boolean) | Get GeoJSON data as a Javascript variable. Called from: rif40_get_geojson_as_js() | Unknown; believed no as used in testing | NO | 1 | 1
| _rif40_getgeolevelextentcommon(character varying, character varying, character varying, integer) | Get bounding box Y max, X max, Y min, X min for <geography> <geolevel view>. Returns: Y max, X max, Y min, X min as a record. Cast to REAL (6 decimal digits precision) | YES | NO | 5 | 1.25
| rif40_closegetmapareaattributecursor(character varying) | Close REF_CURSOR (created by rif40_GetMapAreaAttributeValue). Uses port specific system information functions | YES | YES | 2 | 0.3
| rif40_createmapareaattributesource(character varying, character varying, character varying, character varying, character varying, character varying[]) | Create temporary table with all values for attributes source, attribute names, geography and geolevel select. Uses port specific system information functions | YES | YES | 9 | 2.5
| rif40_deletemapareaattributesource(character varying) | Drop map attribute source (temporary table). Uses port specific system information functions | YES | YES | 3 | 0.75
| rif40_get_geojson_as_js(character varying, character varying, character varying, character varying, boolean, boolean) | Get GeoJSON data as a Javascript variable. Calls: _rif40_get_geojson_as_js() to extract the data | Unknown; believed no as used in testing | NO | 5 | 1.25
| rif40_get_geojson_tiles(character varying, character varying, integer, integer, integer) | Get TopoJSON direct from map tiles table | YES | NO | 1 | 0.3
| rif40_get_geojson_tiles(character varying, character varying, real, real, real, real, integer, boolean, boolean) | Get TopoJSON (if not "X") or GeoJSON for area_ids in map tile. Uses OGSS epecific ST_Centroid(), ST_MakeEnvelope(), ST_X(), ST_Y(); also tile2longitude/latitude() and longitude/latitude2tile() | Unknown; believed no as used in testing | YES | 6 | 2
| rif40_getadjacencymatrix(integer) | Get study area adjacency matrix required by INLA. Uses OGSS specific ST_Touches() | YES | YES | 3 | 1
| rif40_getallattributesforgeolevelattributetheme(character varying, character varying, character varying, character varying[]) | Get all atrributes for geography geolevel theme. The attribute order is the original table order | YES | NO | 3 | 1
| rif40_getgeolevelboundsforarea(character varying, character varying, character varying) | Get bounding box Y max, X max, Y min, X min for <geography> <geolevel view> <map area ID>. Calls: rif40_xml_pkg._rif40_getGeoLevelExtentCommon() | YES | NO | 1 | 0.1
| rif40_getgeolevelfullextent(character varying, character varying) | Get bounding box Y max, X max, Y min, X min for <geography> <geolevel view>; calls: rif40_xml_pkg._rif40_getGeoLevelExtentCommon() | YES | NO | 1 | 0.1
| rif40_getgeolevelfullextentforstudy(character varying, character varying, integer) | Get bounding box Y max, X max, Y min, X min for <geography> <geolevel view> <study>; calls: _rif40_getGeoLevelExtentCommon() | YES | NO | 1 | 0.1
| rif40_getgeometrycolumnnames(character varying) | Get all the SRID 4326 (WGS84) geometry column names for geography | YES | NO | 1 | 0.2
| rif40_getmapareaattributevalue(character varying, refcursor, integer, integer) | Get map attribute data. Return a REFCURSOR as SELECT FROM temporary table. This function returns a REFCURSOR, so only parses the SQL and does not execute it. Offset and row limit are used for cursor contro. Uses port specific system information functions | YES | NO | 3 | 1
| rif40_getmapareas(character varying, character varying, real, real, real, real) | Get area IDs for <geolevel_view> for map area bounding box. Returns JSON: gid, area_id, name. Uses OGSS specific ST_Intersects(), ST_MakeEnvelope() | YES | YES | 4 | 1
| rif40_service_information() | Service Information and version control function | YES | NO | 1 | 0.2
Total |  |  | 17 |  | 50 | 14.05