## People View
Week | Week Starting | PH | DM | BP | Milestone | Notes
14 | 2017-04-03 |  | SQL Server middleware | SQL Server middleware | CDC sandbox ready
15 | 2017-04-10 |  |  |  | Study submission running on SQL server
16 | 2017-04-17 | Assist with middleware (database fixes); SQL Server full install testing
17 | 2017-04-24 |  |  |  | SQL Server RIF complete
18 | 2017-05-01 | CDC Install | CDC Install |  | CDC Install
19 | 2017-05-08 | Background tile download (csache support) | Risk analysis sstaitical requirements
20 | 2017-05-15
21 | 2017-05-22 | UK COA 2011 tiles | Risk analysis
22 | 2017-05-29
23 | 2017-06-05
24 | 2017-06-12 | Not yet allocated (fault fixing) |  | Risk aanlysis R scripts
25 | 2017-06-19
26 | 2017-06-26
27 | 2017-07-03 | Holiday |  | SAHSU RIF data statistical testing | SAHSU RIF operational
28 | 2017-07-10 | http://www.geopedia.si/lite.jsp?params=T118_x408210_y126301_s14#T118_F11063:8283_x405158_y123863_s15_b4
29 | 2017-07-17 |  | Risk analysis integration
30 | 2017-07-24
31 | 2017-07-31
32 | 2017-08-07 |  |  |  | Risk analysis
33 | 2017-08-14 | SAHSU RIF install | SAHSU RIF install | SAHSU RIF install
34 | 2017-08-21 | SAHSU RIF data load |  | SAHSU RIF data load
35 | 2017-08-28
36 | 2017-09-04
37 | 2017-09-11
38 | 2017-09-18
39 | 2017-09-25
40 | 2017-10-02
41 | 2017-10-09
42 | 2017-10-16
43 | 2017-10-23
44 | 2017-10-30
45 | 2017-11-06
46 | 2017-11-13
47 | 2017-11-20
48 | 2017-11-27
49 | 2017-12-04
50 | 2017-12-11
51 | 2017-12-18
52 | 2017-12-25
|  | 2 days/month minimum management |  |  | Public network demonstrator system
Formulas:
Week Starting = DATE(2017,1,-2)-WEEKDAY(DATE(2017,1,3))+[Week]*7