## People View
Week | Week Starting | PH | KG | DM | BP | MD | Milestone | Notes
27 | 2016-07-04 | Shapefile services: 3.1 meta data (6 days) | 2.3 Taxonomy services (4 days) | Data Viewer | Integrate R into Java middleware (10 days)
28 | 2016-07-11 |  |  | Exposomics
29 | 2016-07-18 |  | Integrate R into Java middleware (5 days) | GIS short course | Holiday
30 | 2016-07-25 |  | 2.1 Middleware services planning | Disease Mapping - m/w services (5 days) |  |  | Study Submission
31 | 2016-08-01 | Shapefile services: 3.2 Geospatial outputs (8 days) | Integrate R into Java middleware (10 days) | Handover to new GIS person | Integrate R into Java middleware (10 days)
32 | 2016-08-08 |  |  | Data Viewer - middleware services (5 days)
33 | 2016-08-15 | Holiday | 6.3 Middleware services - create study (14 days) NO PROGRESS DUE TO ILLNESS; Transferred to Peter | Holiday | Holiday
34 | 2016-08-22 | Shapefile services: 3.2 Geospatial outputs II (4 days) |  | 6.1 Taxonomy services, 6.2 Database logon
35 | 2016-08-29 | Shapefile services: 3.3 Get Methods I (6 Days) |  | 6.3 Middleware services - other (4 days) [Potentially Kevin as well] | Not allocated | Holiday to 5th September | Results Viewer (expected 26th September)
36 | 2016-09-05 |  | Not allocated (for overrun - 10 days): now data viewer get methods | Allocated to JG | 8.1 US Test dataset, 8.2 Test Plan, 8.3 Manual calculation of tests | 6.1 Schema comparison (3 days)
37 | 2016-09-12 | 6.2 SQL server schema completion (5 days) |  | 6.3 Middleware services - other (10 days) [Potentially Kevin as well]: data viewer get methods |  | 6.2 SQL server schema completion (as required)
38 | 2016-09-19 |  | ALSPAC |  |  |  | Results Viewer
39 | 2016-09-26 | Shapefile services: 3.3 Get Methods II (6 Days)
40 | 2016-10-03 |  | Calling R; end to end; submission feature | Allocated to JG
41 | 2016-10-10 | Not allocated (for overrun - 9 days): now map tile generation |  | 6.3 Middleware services - other (10 days) [Potentially Kevin as well]: data viewer get methods
42 | 2016-10-17
43 | 2016-10-24
44 | 2016-10-31 |  | ALPSAC | Allocated to JG
45 | 2016-11-07 |  | Java handover, fix submission feature | Disease Mapping
46 | 2016-11-14 |  | Holiday |  |  | Java handover
47 | 2016-11-21 |  | Java handover, fix submission failures |  |  | SQL Server middleware | Results Viewer
48 | 2016-11-28 | SQL Server tile integration | 7. Data Loader (35 days) - start liable for 2/3 weeks delays caused by more work on GET methods | Allocated to JG
49 | 2016-12-05 |  |  | Reamaining data display methods, Java
50 | 2016-12-12
51 | 2016-12-19 | Holiday
52 | 2016-12-26 | Christmas
1 | 2017-01-02 | Postgres and SQL Server tile integration and testing | 7. Data Loader (35 days) - start liable for 2/3 weeks delays caused by more work on GET methods | Documentation, manual |  | Assist Kevin: SQL Server porting issues - middleware query formatter, data loader scripts
2 | 2017-01-09
3 | 2017-01-16
4 | 2017-01-23
5 | 2017-01-30 |  | Holiday |  |  |  | Postgres Data Loader, Postgres install; tileMaker Postgres intrgration
6 | 2017-02-06 | CDC Visit |  |  |  |  | Postgres RIF complete
7 | 2017-02-13 | SQL Server data loader script integration | SQL Server data loader script integration | TopoJSON tiles | Documentation, manual | Transferred to COSMOS/SCAMP | tileMaker SQL Server Integration
8 | 2017-02-20 |  |  | Risk analysis area selection
9 | 2017-02-27 | SQL Server Installer documentation |  |  | US SEER (Cancer) example data |  | Data loader SQL Server install
10 | 2017-03-06 | SQL Server study submission (run study) |  |  |  |  | wpea-traffic/wpea-darwin resdy for install testing
11 | 2017-03-13 |  | Middleware build | SQL Server middleware | SQL Server middleware
12 | 2017-03-20 |  | Leaves for Cabinet Office
13 | 2017-03-27
14 | 2017-04-03 | Assist with middleware (database fixes); SQL Server full install testing |  |  |  |  | CDC sandbox ready
15 | 2017-04-10 | [5 empty] | Study submission running on SQL server
16 | 2017-04-17
17 | 2017-04-24 | [5 empty] | SQL Server RIF complete
18 | 2017-05-01 | CDC Install |  | CDC Install |  |  | CDC Install
19 | 2017-05-08 | Background tile download |  | Risk analysis sstaitical requirements
20 | 2017-05-15
21 | 2017-05-22 | UK COA 2011 tiles |  | Risk analysis area selection
22 | 2017-05-29
23 | 2017-06-05
24 | 2017-06-12 | SAHSU RIF install |  | SAHSU RIF install | SAHSU RIF install
25 | 2017-06-19 | SAHSU RIF data load |  | SAHSU RIF data load
26 | 2017-06-26
27 | 2017-07-03 | Holiday |  |  | SAHSU RIF data statistical testing |  | SAHSU RIF operational
28 | 2017-07-10 | http://www.geopedia.si/lite.jsp?params=T118_x408210_y126301_s14#T118_F11063:8283_x405158_y123863_s15_b4
29 | 2017-07-17 |  |  | Risk aanlysis R scripts
30 | 2017-07-24
31 | 2017-07-31 |  |  | Risk analysis integration
32 | 2017-08-07 | [5 empty] | Risk analysis
|  | 2 days/month minimum management |  |  |  |  | Public network demonstrator system
Formulas:
Week Starting = DATE(2016,1,-2)-WEEKDAY(DATE(2016,1,3))+[Week]*7